## RPT
[5 empty] | Planned |  | % | Actual |  | Status %
| Habib al Mulla project |  |  |  | Start | End |  | Start | End | 20% | 40% | 60% | 80% | 100%
1 | Requirement Gathering and Analysis |  |  |  | 2013-04-10 | 2013-04-19 | 98% | 2013-04-10 | 2013-04-24
| 1.1 | Review Current Capabilities
| 1.2 | Develop the Requirements
| 1.3 | Articulate and Document Requirements
| 1.4 | Refine the Requirements
|  | 1.4.1 |  | Matter Page
|  | 1.4.2 |  | Stage Page
|  | 1.4.3 |  | Case Page
|  | 1.4.4 |  | Hearing Page
|  | 1.4.5 |  | Forecast Page
|  | 1.4.6 |  | Report(5)
|  | 1.4.7 |  | Dashboard
|  | 1.4.8 |  | Security Implementaion
|  | 1.4.9 |  | Setting Page(Normal Steeings)
| 1.5 | Develop the Deliverable
|  | 1.5.1 |  | Matter Page
|  | 1.5.2 |  | Stage Page
|  | 1.5.3 |  | Case Page
|  | 1.5.4 |  | Hearing Page
|  | 1.5.5 |  | Forecast Page
|  | 1.5.6 |  | Report
|  | 1.5.7 |  | Dashboard
|  | 1.5.8 |  | Security Implementaion
|  | 1.5.9 |  | Setting Page(Normal Steeings) |  |  |  |  | 2
2 | Development and Implementation |  |  |  | 2013-04-25 | 2013-07-30 | 50% | 2013-04-25 | 2013-07-27
| 2.1 | Architecture Design + Database |  |  | 2013-04-14 | 2013-04-24 | 98%
| 2.2 | Software Design and Development |  |  | 2013-04-25 | 2013-05-02
|  | Master page design |  |  | 2013-05-06 | 2013-05-23 | 95%
|  | 2.2.1 | Matter Page |  | 2013-05-06 | 2013-05-28 | 95% | 5 days deley due to master page and database changes
|  | 2.2.2 | Stage Page |  | 2013-05-29 | 2013-06-02 | 90%
|  | 2.2.3 | Case page |  | 2013-06-03 | 2013-06-05 | 90%
|  | 2.2.4 | hearing page |  | 2013-06-06 | 2013-06-10 | 90%
|  | 2.2.5 | Forcasting page |  | 2013-06-11 | 2013-06-13 | 90%
|  | 2.2.6 | Report(5 report) |  | 2013-06-16 | 2013-06-21 | 10%
|  | 2.2.7 | Dashboard(4) |  | 2013-06-23 | 2013-07-07 | 50%
|  | 2.2.8 | security implementaion |  | 2013-07-08 | 2013-07-18
|  | 2.2.9 | Settings page(normal settings) |  | 2013-07-20 | 2013-07-25
|  |  | 2.2.7.1 | Process( 3 Screens)
|  |  | 2.2.7.2 | Reports (2 Screens)
|  |  | 2.2.7.3 | Entry (1 Screen)
| 2.3 | Implementation and Integration
| 2.4 | System and Functional Testing |  |  | 2013-07-27 | 2013-09-08 |  | 27-07-2013 + 5 | 2013-08-08
|  | 2.4.1 |  | System Testing
|  | 2.4.2 |  | Bug Fixing
|  | 2.4.3 |  | Integration Testing
|  | 2.5.1 |  | Installation and Configuration of Staging Server
|  | 2.5.2 |  | Deployment of application from progressive Server to client Staging Server
|  | 2.5.3 |  | Complete testing of Application
3 | UAT and Sign Off |  |  |  | 2013-08-08 | 2013-09-08 |  | 08-08-2013+ 5 | 2013-09-08
| 3.1 | UAT Execution
| 3.2 | Gap Analysis and Finalization/Training
| 3.3 | UAT Sign off
4 | Training
| 4.1 | Key User Training
5 | Go Live |  |  |  | 2013-08-08 | 2013-09-08 |  | 08-08-2013 + 5 | 2013-09-08
| 5.1 | Go Live
| 5.2 | Post Go Live Handholding
6 | Handover, Documentation and Final Sign Off |  |  |  | 10-09-2013+ 5